## AWP 2015
Approved at the CCM meeting as of December 13, 2013 (full 3rd project cycle)
Project title: "Support to CCM for 2015", 2nd Project year
Period: 2015 | Budget for YEAR 2: $ 94208
Implementing partner: CCM
Outcome: | Vulnerable groups, especially women, young and aged people, oralmans, people with disabilities have improved access to markets, goods, services and social safety nets
Output: The CCM Secretariat is fully staffed and provides the necessary administrative, secretarial, communication and logistical support to CCM
Outputs | Activities | TIMELINE, estimated dates |  |  |  | Responsible parts
|  | Q5 | Q6 | Q7 | Q8
Oversight activities completed with documented participation by all CCM constituencie
The report with recommendations of Oversight Committee presented to CCM and posted on CCM web-site | Three-day duration field visit to Aktobe oblast to identify progress and gaps in implementation of GFATM Grant. Oversight visits will be conducted by 5 specialists (3 oversight commitee members, 1 finance expert and CCM Secretariat Coordinator): OCAIDS, OTBD, NGO "Onix" |  | April 21-24, 2015 |  |  | Oversight Committee, CCM, MOH, PR, SR
| Three-day duration field visit to Aktau oblast: OCAIDS, OTBD, NGO "Umit" |  | May 25-27, 2015
| JOINT REVIEW VISITS: In 2015 a joint review visit is planned to North - Kazakhstan and Kostanai and Almaty regions. All regions are subsidized from the Republican budget and with no resources for funding from the local budget. Therefore, it is necessary to inform local authorities on the necessity of planning and budgeting from the local budget. Trip for two regions will be held by air, therefore and trip to Taldykorgan will be held by land transport: OCAIDS, OTBD, NGOs: "Pomosh", "Demeu", "Amelia", "Populaton business Found" |  |  |  | June 22-27, 2015
Two reports and presentations on the results of review developed and presented to CCM. | Oversight Committee meeting to revise the PUDRs of PRs on TB and HIV component on the results of 2014, including the review of PR work plans, M&E plans and and results of the annual PRs audit reports. The report of Oversight Committee on the results of review will be presented at the CCM meeting to be held in March 04, 2015 and in May 2015 | February 17, 2015 | April 9, 2015 |  |  | Oversight Committee, CCM Secretariat and technical expert
| Oversight Committee meeting to analyse the reports of SRs determined on the results of the PUDR review |  |  | August 09, 2015
Minutes of the meetings, Declarations on Conflict of Interests are signed and posted at CCM web-site | CCM meeting (joined with CCM capacity building training) will be held in Astana with participation of GMS experts who will inform CCM on the GFATM new requirements &conditions. GMS experts will bring attentions of CCM chair and other members to the necessity of updated Decree on CCM based on the recomendations OIG audit and updated Global Fund requirements within the New Funding Model. At the meeting will take part both PRs and LFAs. Meeting agneda will include issue on the frequency of NGO, RBO, AS and PS selection to CCM. | March 04-05, 2015 |  |  |  | Oversight Committee, CCM members and partners
| CCM meeting will be held in Astana with participation of two PRs and LFAs. At the meeting will be presented the results Oversight reports on review of SRs reports, Oversight visits, CCM project results. Future arrangements on CCM transition plan. Recomendations on mobilization of internal and external resourses. |  |  |  | October 29, 2015
Communication activities to engage constituencies completed by CCM
Advertisements published and posted | Announcement in mass media related to CCM activities according to the recommendations OIG audit. Content for advertisement will be developed by working group established CCM and will be approved by CCM. |  | 2015-12-01 |  |  | CCM Secretariat, CCM, UNDP
| Final package of documents related to the NGO election results that was held in the end of December 2014 will be presented to CCM in February 2015 |  | January 05, 2015
ToR for national consultant and IT company developed; The contract raised; The CCM web-site improved | CCM web -site improvement. Review of CCM web site content by national consultant. This activity includes following steps: |  | June 3-July 31, 2013
| ToR for consultant developed and approved by CCM. |  | June 3, 2013
Individual contract between national consultant and UNDP is signed
Report with recommendations on the improvement of CCM web-site developed and presented at the CCM meeting.
| As a follow up to the recomendations of national consultant the IT company will be recruited |  |  |  |  | CCM Secretariat CCM, UNDP
ToR for IT company developed and approved
Individual contract between IT company and UNDP is signed
CCM web-site is fully operational | CCM documents posted on its web-site on regular basis
CCM members trained on the role of the CCM
Knowledge and skills of CCM members are improved | Two -day duration capacity building training for CCM members on its roles and functions with the involvement of two international consultants and one national consultants. New CCM members will be notified of the updated Global Fund requirements to CCM that will apply to them when eligibility assessment is conducted. Trainers honorarium and travel expenses will be supported by USAID funded GMS project. The ToR for international consultant will be agreed by CCM. TRAINING will be held in the beginning of March 2015. A half of day will be devoted for CCM meeting at the same time the results of the CCM selection will be announced in the CCM meeting. | March 4-5, 2015

## Oversight 2016
Approved at the CCM meeting as of December 13, 2015
Project title: "Support to CCM for 2016", 1st Project year
Period: 2016 | Budget for YEAR 1:
Implementing partner: | CCM, MOHSD and UNDP
Outcome:
Output:
Outputs | Activities | TIMELINE, estimated dates |  |  |  | Total expenditure 2016 | Responsible parts
|  | Q1 | Q2 | Q3 | Q4
Oversight activities completed with documented participation by all CCM constituencie
Reports with recommendations of Oversight Committee presented to CCM and posted on CCM web-site | 2016: Three-day field visit to Astana to identify progress in implementation of the GFATM Grants will be conducted by 5 specialists, including a finance expert – under the IC with UNDP. |  | August 08-12, 2016 |  |  | 9451 | Oversight Committee, CCM, MOH, PR, SR
| Three-day duration field visit to Almaty: CAIDSC, CTBD, NGO "Kazakh Uniion for PLWH", "Zabota", Project Hope. |  |  | September 1-2, 2016 |  | 1191
| Three-day duration field visit to Pavlodar region: OCAIDS, OTBD, OND, NGO "Gerlita", "Ty ne odin" (3 projects) |  |  | September 18-23, 2016 |  | 3640
| Four-day field visit to Aktobe region: RCAIDS, RND, RTBD, Project Hope. |  |  |  | Nov 27-Dec 02, 2016 | 4309
| Two-day field visit to Shymkent: RCAIDS, "Zholdas" Association |  |  |  | Dec 11-14, 2016 | 2213
Three reports and presentations on the results of review are developed and presented to CCM. | Oversight Committee meeting to revise the PUDRs of PRs on TB and HIV component on the results of 2015, including the review of PR work plans, M&E plans and and results of the annual PRs audit reports. The report of Oversight Committee on the results of review will be presented at the CCM meeting to be held in April, July and October 2016 |  | April 21-24, 2016 | 2016-08-01 |  |  | Oversight Committee, CCM Secretariat and technical expert
| Oversight Committee meeting to analyse the reports of SRs determined on the results of the PUDR review |  |  | August 19, 2016
Minutes of the meetings, Declarations on Conflict of Interests are signed and posted at CCM web-site | CCM meeting will be held in Astana with participation of MoHSD, CCM. At the meeting will take part both PRs and LFAs. Meeting agneda will include issue on the selection of CCM Chair. |  | May 18, 2016 |  |  | 10685 | Oversight Committee, CCM members and partners
| CCM meeting on aproval of the request from AFEW to propose a Concept Note on TB prevention in Almaty (on-line) | January 28, 2016
| CCM meeting on approval of the Grant Agreement prolongation on TB grant and its project closure plan (on-line) |  | June 29, 2016
| CCM meeting on signing god abbual declarations | March 04, 2016
CCM meeting on endorsement of the non-costed HIV proposal for 2017 (on-line)
| CCM meeting will be held in Astana with participation of two PRs and LFAs. At the meeting will be presented the results Oversight reports on review of SRs reports, Oversight visits, CCM project results. Future arrangements on CCM transition plan. Recomendations on mobilization of internal and external resourses. |  |  |  | 2016-10-29

## Oversight 2017
Publushed on April 12, 2018
Project title: "Support to CCM for 2018"
Period: 2018
Implementing partner: | CCM, MOHSD and UNDP
Outputs | Activities | TIMELINE, estimated dates |  |  |  | Total expenditure 2018 | Responsible parts
|  | Q1 | Q2 | Q3 | Q4
Oversight activities completed with documented participation by all CCM constituencie
Reports with recommendations of Oversight Committee presented to CCM and posted on CCM web-site | 2018: Four-day field visit to Kokshetau to identify progress in implementation of the GFATM Grants will be conducted by 5 specialists, including a finance expert – under the IC with UNDP. | July 02-06,2018 |  |  |  | 6150 | Oversight Committee, CCM, MOH, PR, SR
| Five-day duration field visit to Karagandy: OCAIDSC, CTBD, NGO "Umit", "Shapagat", "Moi Dom", NGO "Gala" |  |  | July 23-28, 2018 |  | 4920
| Five-day duration field visit to Shymkent: OCAIDSC, CTBD, NGO "Zholdas", "Aiana" |  |  | August 20-25, 2018
| Three-day duration field visit to West - Kazkahstan region: OCAIDS, OTBD, NGOs if available |  |  | September 17-21, 2018 |  | 5572
Three reports and presentations on the results of review are developed and presented to CCM. | Oversight Committee meeting to revise the PUDRs of PRs on TB and HIV component on the results of 2017, including the review of PR work plans, M&E plans and and results of the annual PRs audit reports. The report of Oversight Committee on the results of review will be presented at the CCM meeting to be held in October 2018 |  |  | Jun 25, 2018 |  |  | Oversight Committee, CCM Secretariat and technical expert
| Oversight Committee meeting to analyse the reports of SRs determined on the results of the PUDR review |  |  |  | October 2-3, 2018
Minutes of the meetings, Declarations on Conflict of Interests are signed and posted at CCM web-site | CCM meeting will be held in Astana with participation of MoHSD, CCM. At the meeting will take part both PRs and LFAs. Meeting agneda will include: 1) development of TB proposal for 2020-2022; 2) TB/HIV regional proposals and etc. | April 12, 2018 |  |  |  | 11930 | Oversight Committee, CCM members and partners
| CCM meeting on endorsement of saving on TB grant |  | April 12.2018
| CCM meeting on signing of annual declarations on CoI | April 12, 2018
| CCM meeting will be held in Astana with participation of two PRs and LFAs. At the meeting will be presented the results Oversight reports on review of SRs reports, Oversight visits, CCM project results. Future arrangements on CCM transition plan. Recomendations on mobilization of internal and external resourses. |  |  |  | 2018-10-26

## Oversight 2018
Publushed on April 12, 2018
Project title: "Support to CCM for 2018"
Period: 2018
Implementing partner: | CCM, MOHSD and UNDP
Outputs | Activities | TIMELINE, estimated dates |  |  |  | Total expenditure 2018 | Responsible parts
|  | Q1 | Q2 | Q3 | Q4
Oversight activities completed with documented participation by all CCM constituencie
Reports with recommendations of Oversight Committee presented to CCM and posted on CCM web-site | 2018: Four-day field visit to Kokshetau to identify progress in implementation of the GFATM Grants will be conducted by 5 specialists, including a finance expert – under the IC with UNDP. | July 02-06,2018 |  |  |  | 5245 | Oversight Committee, CCM, MOH, PR, SR
| Five-day duration field visit to Karagandy: OCAIDSC, CTBD, NGO "Umit", "Shapagat", "Moi Dom", NGO "Gala" |  |  | July 23-28, 2018 |  | 5145
| Five-day duration field visit to Shymkent: OCAIDSC, CTBD, NGO "Zholdas", "Aiana" |  |  | August 20-25, 2018 |  | 4995
| Three-day duration field visit to West - Kazkahstan region: OCAIDS, OTBD, NGOs if available |  |  | September 17-21, 2018 |  | 5345
Three reports and presentations on the results of review are developed and presented to CCM. | Oversight Committee meeting to revise the PUDRs of PRs on TB and HIV component on the results of 2017, including the review of PR work plans, M&E plans and and results of the annual PRs audit reports. The report of Oversight Committee on the results of review will be presented at the CCM meeting to be held in October 2018 |  |  | Jun 25, 2018 |  |  | Oversight Committee, CCM Secretariat and technical expert
| Oversight Committee meeting to analyse the reports of SRs determined on the results of the PUDR review |  |  |  | October 2-3, 2018
Minutes of the meetings, Declarations on Conflict of Interests are signed and posted at CCM web-site | CCM meeting will be held in Astana with participation of MoHSD, CCM. At the meeting will take part both PRs and LFAs. Meeting agneda will include: 1) development of TB proposal for 2020-2022; 2) TB/HIV regional proposals and etc. | April 12, 2018 |  |  |  | 18600 | Oversight Committee, CCM members and partners
| CCM meeting on endorsement of saving on TB grant |  | April 12.2018
| CCM meeting on signing of annual declarations on CoI | April 12, 2018
| CCM meeting will be held in Astana with participation of two PRs and LFAs. At the meeting will be presented the results Oversight reports on review of SRs reports, Oversight visits, CCM project results. Future arrangements on CCM transition plan. Recomendations on mobilization of internal and external resourses. |  |  |  | 2018-10-26